## 📋 Index
Edmonton Photographer Marketplace — Phase 1 Page Reference
# | Page / Route | Domain | Auth Required | Sprint | Rendering | Priority | Status
1 | / | Shared | No | S8 | SSG | P0 | To Build
2 | /login | Shared | No | S1 | CSR | P0 | To Build
3 | /signup | Shared | No | S1 | CSR | P0 | To Build
4 | /photographers | Client | No | S3 | SSR | P0 | To Build
5 | /photographers/[username] | Client | No | S3 | SSR | P0 | To Build
6 | /inbox | Client | Yes | S4 | CSR | P1 | To Build
7 | /inbox/[conversationId] | Client | Yes | S4 | CSR | P1 | To Build
8 | /account/settings | Client | Yes | S7 | CSR | P2 | To Build
9 | /onboarding | Photographer | Yes | S1 | CSR | P0 | To Build
10 | /pending | Photographer | Yes | S1 | CSR | P0 | To Build
11 | /dashboard | Photographer | Yes | S2 | SSR | P0 | To Build
12 | /dashboard/profile | Photographer | Yes | S2 | CSR | P0 | To Build
13 | /dashboard/portfolio | Photographer | Yes | S2 | CSR | P0 | To Build
14 | /dashboard/portfolio/[albumId] | Photographer | Yes | S2 | CSR | P1 | To Build
15 | /dashboard/trust | Photographer | Yes | S5 | CSR | P0 | To Build
16 | /dashboard/inbox | Photographer | Yes | S4 | CSR | P1 | To Build
17 | /dashboard/inbox/[conversationId] | Photographer | Yes | S4 | CSR | P1 | To Build
18 | /dashboard/settings | Photographer | Yes | S7 | CSR | P2 | To Build
19 | /admin | Admin | Admin | S7 | SSR | P1 | To Build
20 | /admin/approvals | Admin | Admin | S7 | CSR | P0 | To Build
21 | /admin/accounts | Admin | Admin | S7 | CSR | P1 | To Build
22 | /admin/conversations | Admin | Admin | S7 | CSR | P2 | To Build
23 | /admin/trust-health | Admin | Admin | S6 | CSR | P1 | To Build

## 🔗 Shared Pages
Shared Pages — Auth & Public
/ — Homepage
Description | Marketing homepage. SSG rendered. Entry point for all new visitors.
Features | • Nav: logo, Browse photographers link, List your work CTA (no login button) • Hero: short headline, specialty dropdown + Edmonton location, Search/Browse CTA button • Stats strip: photographer count, specialties count, Edmonton-local badge • Featured photographers: 3 cards (photo, name, specialty, trust score, starting rate) • Specialty shortcuts: icon grid — Wedding, Portrait, Corporate, Real Estate, Events, Newborn • How it works: 3 steps for clients (Search → View profiles → Message) • Photographer CTA section: 'List your work for free' → /signup • Footer: minimal — no newsletter, no social links • Zero login prompts — fully public browsing • SEO: meta title, description, OG image, structured data for local business
Dev Notes | No newsletter or subscribe CTA anywhere. Search bar should auto-focus on load.
/login — Login
Description | Unified login for both client and photographer roles.
Features | • Email + password login form • Google OAuth one-click button • Role-aware redirect after login: clients → /photographers, photographers → /dashboard • Forgot password link → triggers Resend email flow • Link to /signup for new users • Error states: wrong password, unverified email, account suspended • Redirect preservation: if user was trying to message, redirect back to that conversation after login • No role selector — role is stored on the account
Dev Notes | Most common entry point after clicking Message on a photographer profile. Preserve ?redirect= param.
/signup — Sign up
Description | Role selection + registration. Branches into client or photographer flows.
Features | • Role selector: two clear options — 'I'm looking for a photographer' vs 'I'm a photographer' • Email + password fields • Google OAuth button • Terms of service checkbox (link to /terms) • Client path: account created immediately, redirect to /photographers or original destination • Photographer path: account created, redirect to /onboarding step 1 • Inline validation: email format, password strength (min 8 chars) • Duplicate email error state • No newsletter opt-in anywhere on this page
Dev Notes | Keep it minimal. No welcome email with marketing. Confirmation email only.

## 👤 Client Pages
Client Domain Pages
/photographers — Browse photographers
Description | Main discovery page. Fully public. Primary traffic destination from homepage search.
Features | • Search bar: full-text across names, bios, specialty tags (Postgres FTS) • Filter panel: specialty (multi-select), price range slider, Edmonton neighbourhood • Sort options: Trust score (default), Recently joined, Most active • Photographer cards: profile photo, name, specialties, trust score badge, starting rate, online indicator • Card click → /photographers/[username] • Empty state: no results message + clear filters button • Result count display: 'Showing 42 photographers' • Pagination or infinite scroll (recommend pagination for SEO) • URL reflects active filters (?specialty=wedding&sort=trust) for shareable links • No login required — zero friction browsing • Mobile: stack cards to single column
Dev Notes | SSR for SEO. Filter state in URL params. Postgres FTS sufficient for <500 photographers.
/photographers/[username] — Photographer public profile
Description | The core conversion page. Every element builds trust and leads to Message.
Features | • Profile header: cover photo, avatar, name, location, specialties badges, online status dot • Trust score: large composite score display, breakdown bar per source (Google/Yelp/Instagram/Facebook) • External source badges: linked icons for each connected platform with their individual score • Bio section: about text, years of experience, photography style • Rates: starting rate, rate type (per hour/session/day), availability notes • Portfolio gallery: albums grid, click album → photo lightbox • Reviews section: pulled from external sources with attribution (Google, Yelp) • Message button: sticky CTA — if logged in → opens chat, if not → redirect to /signup?redirect=back • Back to browse link (preserves search state) • Share button: copy profile URL • No newsletter or follow CTA • SEO: photographer name in title, OG image from cover photo
Dev Notes | Message button is THE only auth trigger. Never gate portfolio or trust score. SSR for SEO.
/inbox — Client chat inbox
Description | Lists all active conversations. Auth required.
Features | • Conversation list: photographer avatar, name, last message preview, timestamp, unread count badge • Sort: most recent message first • Unread conversations visually distinct (bold name, colored badge) • Click conversation → /inbox/[conversationId] • Empty state: 'No conversations yet. Browse photographers to get started.' + Browse link • Real-time unread count in nav badge • Search conversations (by photographer name) • Mobile: full-width list view
Dev Notes | Supabase Realtime subscription opened on mount. Nav badge updates via global subscription.
/inbox/[conversationId] — Chat thread (client)
Description | Real-time messaging thread between client and photographer.
Features | • Thread header: photographer avatar, name, specialty, online status ('Online now' / 'Active X min ago') • Message bubbles: iMessage style — client right (teal), photographer left (gray) • Timestamps on messages (relative: 'just now', '5 min ago', then date for older) • Read receipts: 'Seen' indicator under last sent message • Message input: textarea, send on Enter or button click • Real-time delivery via Supabase Realtime websocket • Email fallback: if photographer offline 5+ min, Resend email notification sent • Link to photographer's public profile in header • Back to inbox link • Messages load newest at bottom, scroll to bottom on new message • Typing indicator (optional Phase 1 enhancement)
Dev Notes | Supabase Realtime channel per conversation. messages table: id, conversation_id, sender_id, content, created_at, read_at.
/account/settings — Client account settings
Description | Personal account management for clients.
Features | • Display name edit • Email address display (non-editable without re-auth flow) • Change password form (current + new + confirm) • Notification preferences: email on new message toggle • Online presence toggle: appear offline to photographers • Danger zone: Delete account (with confirmation modal) • Save changes button with success/error feedback
Dev Notes | Sprint 7. Not a launch blocker. Simple form page.

## 📸 Photographer Pages
Photographer Domain Pages
/onboarding — 6-step onboarding flow
Description | Multi-step flow to create a complete photographer listing. Progress saved per step. Modelled on Airbnb host onboarding.
Features | • Step 1 — Basic info: full name, display name, city (pre-filled Edmonton), neighbourhood dropdown • Step 2 — Specialties: photography categories multi-select (Wedding/Portrait/Corporate/Real Estate/Events/Newborn/Street), experience level radio, years active • Step 3 — Portfolio upload: drag & drop to R2, album name input, min 3 photos required, cover photo selection, progress bar during upload • Step 4 — Rates & availability: starting rate input, rate type select (per hour/session/day), availability notes textarea — all optional • Step 5 — Connect your presence: Google Business URL, Instagram handle, Yelp URL, Facebook URL — all optional but encouraged • Step 6 — Review & publish: completeness score percentage, preview of public profile, submit for admin review button • Progress bar at top showing current step of 6 • Back/Next navigation between steps • Auto-save: each step saves independently on Next click • Return flow: if photographer leaves mid-onboarding, resumes at last saved step • Completeness score live-updates as fields filled • Submit triggers email to admin + confirmation email to photographer
Dev Notes | Single route /onboarding with step state in URL (?step=3) or React state. R2 upload via pre-signed URLs.
/pending — Pending approval screen
Description | Holding page shown after onboarding submission while admin reviews the account.
Features | • Clear status message: 'Your profile is under review' • Estimated review time (e.g. 'Usually within 24 hours') • What happens next explanation (3 bullet points) • Contact email for questions • Edit profile link (allows editing before approval) • Auto-redirect to /dashboard when account status changes to approved • Email sent when approved/rejected (via Resend)
Dev Notes | Simple status page. Supabase realtime can push status change to trigger redirect without polling.
/dashboard — Photographer dashboard home
Description | Overview hub for the photographer. First page after login for approved photographers.
Features | • Welcome header: avatar, display name, 'Your profile is live' status badge • Profile completeness score card: percentage + 'Complete your profile' prompt if < 80% • Quick stats row: total profile views (all time), messages received, trust score • Unread messages card: count + link to inbox • Trust aggregator summary: composite score, last sync time, link to /dashboard/trust • Portfolio summary: album count, photo count, link to /dashboard/portfolio • Quick links: Edit profile, Upload photos, View my public profile (opens in new tab) • Recent activity feed: last 5 messages or profile views
Dev Notes | SSR for initial load. Stats from Supabase queries. Online status managed via Realtime Presence.
/dashboard/profile — Edit public profile
Description | Full profile editor. Changes reflect live on the public profile page.
Features | • Display name field • Bio / about text textarea (500 char limit, live counter) • Location: city (locked to Edmonton Phase 1), neighbourhood dropdown • Specialties: same multi-select as onboarding • Experience level and years active • Starting rate + rate type select • Availability notes textarea • Profile photo upload (separate from portfolio — this is the avatar) • Cover photo upload • External platform links: Google, Instagram, Yelp, Facebook URLs • Live preview panel: shows how public profile will look • Save changes button: optimistic update, error rollback • Unsaved changes warning on navigation away
Dev Notes | Profile photo and cover stored in R2 under photographer's folder. Public profile updates after save.
/dashboard/portfolio — Portfolio manager
Description | Top-level portfolio view — manage albums, upload photos, set covers.
Features | • Albums grid: album cover thumbnail, name, photo count • Create new album: name input modal, then redirect to album editor • Album card actions: rename, set as profile cover, delete (with confirmation) • Drag to reorder albums (order reflects on public profile) • Overall portfolio stats: total photos, total albums, storage used • Upload photos button: opens file picker, multi-select, uploads to R2 • Photos unassigned to album land in 'General' default album • Click album → /dashboard/portfolio/[albumId] • Min 3 photos reminder if below threshold
Dev Notes | R2 upload via pre-signed URLs generated server-side. File size limit 10MB per photo.
/dashboard/portfolio/[albumId] — Album editor
Description | Edit a single album — photos, order, cover, name.
Features | • Album name edit (inline edit on click) • Photo grid: thumbnails with drag-to-reorder • Upload more photos: drag & drop zone + file picker • Per-photo actions: set as album cover, delete (with confirmation) • Upload progress indicator per file • Back to portfolio link • Delete album button (moves photos to General or deletes) • Photo count + storage size display • Empty state: 'No photos yet. Upload some to get started.'
Dev Notes | Drag & drop reorder via react-dnd or @dnd-kit. Order saved as integer position in DB.
/dashboard/trust — Trust aggregator
Description | Connect external platforms, view composite score, see synced reviews.
Features | • Composite score display: large number, visual breakdown ring or bar per source • Source cards: Google, Instagram, Yelp, Facebook — each showing connection status • Connect flow per source: paste URL/handle → save → triggers first sync • Per-source data preview: star rating, review count, last 3 reviews shown • Instagram: follower count, last 9 post thumbnails • Last sync timestamp per source • Manual re-sync button (rate limited: once per hour) • Score weight explanation: tooltip showing % weight each source carries • 'Your score vs platform average' comparison (once data exists) • Unconnected sources highlighted with 'Connect to boost your score' nudge
Dev Notes | Vercel Cron syncs every 24h. Facebook may be in soft mode (link only) until Meta app review.
/dashboard/inbox — Photographer chat inbox
Description | All client conversations for the photographer.
Features | • Conversation list: client avatar (initials), name, last message preview, timestamp, unread badge • Sort: most recent first • Unread conversations visually distinct • Click → /dashboard/inbox/[conversationId] • Empty state: 'No messages yet. Your profile is live — clients will reach out soon.' • Cannot initiate a conversation — receive only • Global unread count in nav • Search by client name
Dev Notes | Photographer cannot start conversations — prevents spam. First message always from client.
/dashboard/inbox/[conversationId] — Chat thread (photographer)
Description | Real-time chat thread — same tech as client side, photographer perspective.
Features | • Thread header: client name, online status • Message bubbles: photographer right (teal), client left (gray) • Timestamps + read receipts • Message input: textarea, send on Enter or button • Real-time via Supabase Realtime • Email notification to client when photographer replies (if offline) • Link to client's account (name only — no public client profiles) • Back to inbox link • Flag conversation button (sends to admin moderation queue)
Dev Notes | Same Supabase channel as client thread. flag_conversation triggers admin notification.
/dashboard/settings — Photographer account settings
Description | Account-level settings — not profile content (that's /dashboard/profile).
Features | • Display name • Email (non-editable without re-auth) • Change password • Notification preferences: email on new message, email on approval status change • Online presence toggle: appear offline • Public profile link: copy link button • Account status badge: Approved / Pending / Suspended • Danger zone: delete account (irreversible, requires typed confirmation)
Dev Notes | Keep separate from /dashboard/profile which is about the public-facing content.

## 🛡️ Admin Pages
Admin Domain Pages
/admin — Metrics dashboard
Description | Platform health overview. Admin-only. Primary monitoring page.
Features | • Photographer stats: total registered, pending approval, live, suspended — stat cards • Client stats: total registered, active this week • Daily growth chart: signups per day (last 30 days) — line chart • Messages sent per day chart (last 14 days) • Search queries per day + top 10 search terms table • Portfolio stats: total photos uploaded, average per photographer, total storage (R2) • Profile quality distribution: completeness score histogram • Trust aggregator stats: % photographers with 0 / 1 / 2+ sources connected • Quick action links: Go to approvals queue, Go to accounts • Last updated timestamp (auto-refresh every 5 min)
Dev Notes | Read-only. Queries can be expensive — consider materialized views or caching for production.
/admin/approvals — Photographer approval queue
Description | Review and action pending photographer registrations.
Features | • Queue count badge: 'X pending' • Photographer cards: profile photo, name, email, submitted date, specialties • Completeness score shown per application • Portfolio thumbnails preview (first 6 photos) • Trust sources submitted: which platforms they connected • Initial trust score from first aggregator fetch • Action buttons: Approve (green), Reject with reason (red), Request changes (amber) • Reject modal: reason select (inappropriate content / incomplete / spam / other) + free text • Request changes modal: free text message sent to photographer email • Approve action: sends welcome email, sets status to live, profile goes public • Filter: All / Oldest first / Highest completeness • Bulk approve button (for high-volume periods)
Dev Notes | Approval email via Resend. Rejection email includes reason. Status: pending → approved/rejected.
/admin/accounts — Account manager
Description | Search, inspect, and moderate any account on the platform.
Features | • Search bar: search by name, email, username across all accounts • Role filter tabs: All / Clients / Photographers • Account cards: avatar, name, email, role, status badge, join date, last active • Account detail view: full profile preview, activity log • Per-account actions: Suspend (temporary), Ban (permanent), Unsuspend, Delete • Suspension modal: reason + duration (1 day / 7 days / 30 days / permanent) • Photo moderation: view portfolio, remove individual photos with reason • Flag for review: adds to a review queue • Account status history log: who took what action when • View as user: preview what their public profile looks like
Dev Notes | All moderation actions logged with admin ID + timestamp. Reversible actions have undo window.
/admin/conversations — Conversation browser
Description | Read and moderate any conversation for dispute resolution.
Features | • Search: by client name, photographer name, or message content • Conversation list: pair names, message count, last activity, flagged badge • Flagged conversations filter: show only flagged • Full conversation thread view: read-only, all messages with timestamps • Freeze conversation: prevent new messages (with reason logged) • Unfreeze conversation • Delete specific message (admin only) • Export conversation log (CSV) for records • Link to both participants' account pages • Message volume chart: messages per day (last 7 days)
Dev Notes | Read-only view. Freeze/unfreeze is the main moderation action. Full audit log.
/admin/trust-health — Trust aggregator health panel
Description | Monitor the sync status of the trust aggregator across all photographers.
Features | • Per-source status table: Google / Instagram / Yelp / Facebook — last sync time, success rate, fail count • Rate limit warnings: banner if any source hitting API limits • Sync error log: list of failed syncs with error type and photographer • Composite score distribution chart: histogram of scores across all photographers • Zero-source photographers list: names + email for outreach priority • Manual trigger: re-run sync for a specific photographer • Cron schedule display: next scheduled run time • API quota remaining (Google Places $200 credit usage estimate) • Sync success rate over last 7 days per source
Dev Notes | Google Places has $200/month free credit. At 50 photographers syncing daily, well within limits.

## 🗓️ Sprint Plan
Phase 1 Sprint Build Order — 8 Sprints × 2 Weeks
Sprint | Weeks | Pages Built | Key Technical Work | Deliverable
S1 | 1–2 | /login, /signup, /onboarding (steps 1–2), /pending | Supabase auth, roles, DB schema (users/photographers/clients), email confirmation via Resend | Auth working, role routing, onboarding steps 1–2
S2 | 3–4 | /onboarding (steps 3–4), /dashboard, /dashboard/profile, /dashboard/portfolio | R2 photo upload (pre-signed URLs), album/photo DB schema, profile CRUD, dashboard stats queries | Photographer can complete profile + upload photos
S3 | 5–6 | /photographers, /photographers/[username], /onboarding (steps 5–6) | Postgres FTS setup, filter/sort queries, public profile SSR, portfolio gallery, specialty tags | Clients can browse and view profiles
S4 | 7–8 | /inbox, /inbox/[conversationId], /dashboard/inbox, /dashboard/inbox/[conversationId] | Supabase Realtime channels, conversations + messages schema, read receipts, Realtime Presence (online status), Resend offline email fallback | Full real-time chat working both sides
S5 | 9–10 | /dashboard/trust (Google + Instagram connectors) | Google Places API integration, Instagram Basic Display API, composite score calculation, trust score display on public profile | Trust aggregator live for 2 sources
S6 | 11–12 | /dashboard/trust (Yelp + Facebook), /dashboard/portfolio/[albumId] | Yelp Fusion API, Facebook Graph API (soft mode), Vercel Cron sync scheduler, deduplication logic, album editor drag-to-reorder | Full trust aggregator + cron sync
S7 | 13–14 | /admin, /admin/approvals, /admin/accounts, /admin/conversations, /account/settings, /dashboard/settings | Admin role + middleware, approval queue logic, account moderation actions, conversation browser, settings CRUD | Admin can approve photographers, platform is moderatable
S8 | 15–16 | / (homepage), /admin/trust-health — polish pass all pages | Homepage SSG, trust aggregator health panel, completeness score polish, QA full flow, performance audit | Platform launch-ready

## 🗄️ DB Schema
Supabase Database Schema Reference — Core Tables
Table / Column | Type | Constraint | Description | Used By Pages
── TABLE: users ── |  |  | Supabase Auth users table (managed)
id | uuid | PK | Auth user ID | All auth pages
email | text | unique | Login email | Login, signup, settings
role | text | not null | client ¦ photographer ¦ admin | All pages — routing
created_at | timestamptz | default now() | Account creation time | Admin dashboard
── TABLE: photographer_profiles ── |  |  | Public photographer data
id | uuid | PK, FK→users.id | Links to auth user | All photographer pages
display_name | text | not null | Public name shown on profile | Profile, browse, chat
bio | text |  | About text (500 char max) | Profile page
neighbourhood | text |  | Edmonton neighbourhood | Browse filters
specialties | text[] |  | Array of specialty tags | Browse, profile
experience_level | text |  | beginner ¦ intermediate ¦ professional | Profile
years_active | int |  | Years shooting | Profile
starting_rate | numeric |  | Lowest advertised rate | Browse cards, profile
rate_type | text |  | per_hour ¦ per_session ¦ per_day | Profile
availability_notes | text |  | Free text availability | Profile
status | text | default pending | pending ¦ approved ¦ suspended ¦ banned | Admin, onboarding
completeness_score | int |  | 0–100, calculated on save | Dashboard, search ranking
avatar_url | text |  | R2 URL for profile photo | Browse cards, profile, chat
cover_url | text |  | R2 URL for profile cover | Profile page
trust_score | numeric |  | Composite score 0–5 | Browse sort, profile display
onboarding_step | int | default 1 | Last completed step (1–6) | Onboarding resume
created_at | timestamptz | default now() | Profile creation | Admin
updated_at | timestamptz |  | Last edit | Cache invalidation
── TABLE: external_platforms ── |  |  | Connected trust aggregator sources
id | uuid | PK
photographer_id | uuid | FK→photographer_profiles.id |  | Trust dashboard
platform | text | not null | google ¦ instagram ¦ yelp ¦ facebook | Trust dashboard
url_or_handle | text |  | URL or @ handle provided by photographer | Trust dashboard
rating | numeric |  | Platform star rating (normalised 0–5) | Trust score calc
review_count | int |  | Total reviews on platform | Trust display
follower_count | int |  | Instagram followers | Trust display
raw_data | jsonb |  | Full API response cached | Sync scheduler
last_synced_at | timestamptz |  | Last successful sync | Admin trust health
sync_status | text |  | success ¦ failed ¦ rate_limited | Admin trust health
── TABLE: albums ── |  |  | Portfolio albums
id | uuid | PK |  | Portfolio pages
photographer_id | uuid | FK |  | Portfolio
name | text | not null | Album display name | Portfolio
cover_photo_id | uuid | FK→photos.id | Album cover | Portfolio grid
position | int |  | Display order (drag to reorder) | Portfolio
created_at | timestamptz
── TABLE: photos ── |  |  | Individual portfolio photos
id | uuid | PK |  | Portfolio pages
album_id | uuid | FK→albums.id |  | Album editor
photographer_id | uuid | FK
r2_url | text | not null | Cloudflare R2 object URL | Portfolio, profile
position | int |  | Order within album | Album editor
uploaded_at | timestamptz
── TABLE: conversations ── |  |  | Chat conversation pairs
id | uuid | PK |  | Inbox pages
client_id | uuid | FK→users.id |  | Client inbox
photographer_id | uuid | FK→photographer_profiles.id |  | Photographer inbox
created_at | timestamptz |  | When first message sent | Inbox list
last_message_at | timestamptz |  | For sort order | Inbox list
is_frozen | bool | default false | Admin freeze flag | Admin conversations
── TABLE: messages ── |  |  | Individual chat messages
id | uuid | PK |  | Chat thread
conversation_id | uuid | FK→conversations.id |  | Chat thread
sender_id | uuid | FK→users.id |  | Chat thread
sender_role | text |  | client ¦ photographer | Chat bubble alignment
content | text | not null | Message body | Chat thread
created_at | timestamptz | default now() |  | Timestamps
read_at | timestamptz |  | null = unread | Read receipts, unread count

## ⚙️ Tech Stack
Technology Stack & Infrastructure Reference
Layer | Technology | Plan / Cost | Purpose & Notes | Relevant Pages
Frontend + API | Next.js 14 (App Router) | Open source | SSR/SSG/CSR, API routes, edge middleware. Purpose-built for Vercel. | All pages
Hosting | Vercel Pro | $20/month | Native Next.js, edge CDN, built-in Cron jobs for trust aggregator, preview deploys. | All pages
Database | Supabase | Free tier | Postgres + Row Level Security + Realtime websockets + Auth. 500MB DB, 50k MAU free. | All pages with data
Authentication | Supabase Auth | Included | Email/password + Google OAuth. JWT tokens. Role stored in user metadata. | /login, /signup
Photo storage | Cloudflare R2 | Free tier | 10GB free, no egress fees, S3-compatible API. Pre-signed URLs for client-side upload. | /dashboard/portfolio, profile
Email | Resend | Free tier | 3,000 emails/month free. Approval emails, welcome emails, offline chat notifications. | Chat, onboarding, admin
Real-time chat | Supabase Realtime | Included | Websocket channels per conversation. Presence for online status. 200 concurrent on free. | /inbox, /dashboard/inbox
Background jobs | Vercel Cron | Included | Trust aggregator sync runs every 24h per photographer. No BullMQ needed. | /admin/trust-health
Search | Postgres FTS | Included | Full-text search across names/bios/tags. Sufficient for <500 photographers. | /photographers
Trust: Google | Google Places API | $200 free/mo | Star rating, review count, last 10 reviews. Well within free credit at 50 photographers. | /dashboard/trust
Trust: Instagram | Basic Display API | Free | Latest 9 posts, follower count. Own posts only (not tagged). | /dashboard/trust
Trust: Yelp | Yelp Fusion API | Free tier | Star rating, review count, last 5 reviews. Daily sync within free limits at 50 photographers. | /dashboard/trust
Trust: Facebook | Graph API | Free | Page rating + recommendations. Requires Meta app review — soft mode (link only) at launch. | /dashboard/trust
CSS framework | Tailwind CSS | Open source | Utility-first. Used for all custom styling. | All pages
Component library | shadcn/ui | Open source | Admin + dashboard pages. Radix UI primitives + Tailwind. Copy-paste, fully owned. | Dashboard, admin
Domain | .ca domain | $15/year | Edmonton-local positioning. | All pages